## Slide 1: Basic Project Initiating and Reporting Tools
Tool Name | Purpose | Key Uses
Project Charter | Ensure alignment between key stakeholders regarding project parameters | Drive organizational alignment (especially in early project stages)
Project Timeline | Itemize project milestones on a simple visual | Inform Project Update Clarify dependency impacts
Project Update | Provide key project guardrails and status on a single slide | Guide DS Team and Portfolio Meetings Provide simple reference for other Data Science team members re: project status
Risks and Issues Log | Proactively monitor and address risks and issues | Mitigate key risks before they materialize Track issues to resolution
Use these tools for every project effort

## Slide 2: Project Charter (Example: 1 of 3)
Problem Statement
There is presently no measure of consistency in the Severity Adjusted Dashboard.
Financial Benefits | Operational Benefits | Client Impacts | Patient Impacts
[not for DS to “sign off”] | Improved contract performance | Improved financial performance | Improved outcomes through improved focus on LOS and Discharge Assessment, particularly
Goal Statement
Provide a measure of consistency in the Severity Adjusted Dashboard for mature clients
Value / Benefits
🗹
This is a very basic charter template. For more complex projects with broader organizational reach, a more in-depth template may be necessary.

## Slide 3: Project Charter (Example: 2 of 3)
Dimension | In Scope | Out of Scope
Systems | SADB | 
Datasets | CM SMTX | 
Processes |  | 
Functions / Departments |  | 
Clients | Mature clients (definition TBD by stakeholders) | 
Other | Best Practice Data Set: To be used as reference point for opportunity estimation | 
Scope

## Slide 4: Project Charter (Example: 3 of 3)
Name | Organizational Title | Project Role
Jane Doe | VP, Network | Project Sponsor
John Smith | Network Data Analyst | Data SME
Anne Ford | Data Science Analyst | Data Science Project Lead
Brian Jones | Director, Operations | Opportunity Estimation SME
Jen Sanders | Director, Clinical Outcomes | Clinical SME
Deliverables
Deliverable | Assignee | Key Requirements
Calculated opportunity in terms of projected incremental revenue | A Ford | Signed off on by B Jones
Project Team
Description | Implications if Invalid | Validation Plan (include contact) | Target Date Date Validated
We can treat BPCI and health plan clients the same | Need to form separate plans for BPCI and health plan | Form strategy based on discussion with Amy L | Target: 2/16/18 Actual:
Assumptions

## Slide 5: Project Timeline (Example)
 | Jan 18 | Feb 18 | Mar 18 | Apr 18 | May 18 | Jun 18
R&D Project |  |  |  |  |  | 
Enterprise Project |  |  |  |  |  | 
Maintenance and Support |  |  |  |  |  | 
Milestone
Critical Point/Task
All milestones should be shown on the timeline
Use simple verb-object structure for milestones
Milestones on timeline should align to the milestones on the project update
Show key dependencies for critical tasks using arrows when necessary
Complex projects may warrant a full-scale project plan
Complete draft model
Concept approval
Incorporate model feedback
Finalize requirements
Finalize development
Finalize
design
Complete
UAT
Launch prototype
Launch
MVP
Train
QA Staff

## Slide 6: Project Update
Risk / Issue / Decision Description | Mitigation Plan | Target Date | Status | Responsible
Decision: Clinical approval to proceed with proposed architectural concept | Present to Amy L and Colleen O’Rourke / designee for approval | 2/12/18 |  | A. Curtis
Project Name: nH Match
Description:
Create a decision support tool for Discharge Planning (integrated into nH Discharge, nH Coordinate, or both) to display the top SNFs for a patient’s specific needs based on: Case 1: historical performance for similar patients when sufficient nH market data are available Case 2: the nH Perform score of SNFs when either: insufficient nH market data are available, or Predict assessment was not conducted
Primary Goal:
Provide decision makers a framework for identifying SNFs with potential for best outcomes for the patient, tailored for each patient’s needs if market data are available, else using publicly available data (nH Perform)
Recent / Upcoming Milestones:
Key Scope Elements:
Creation of a working mockup / proof of concept to be approved for product development. Selection of factors, including severity adjusters (current factors shown in “Use Cases”). Actual factors TBD based on discussions w/ clinical subject matter experts. Scoring method
Milestone | Target Date | Status | Responsible
Demo concept to DS Strg Cmte | 1/19/18 |  | M. Lanius
Get approval on MGPP and architectural concept | 1/29/18 |  | Curtis
Get Amy L input on model inputs and scoring | 2/5/18 |  | A. Curtis
Not Started | On Track | At Risk | Delayed | Complete
Legend for Status:
Risks, Issues and Decisions
Sponsor
Colleen O’Rourke
Subject Matter Experts (SMEs)
Clinical: Amy Leibensberger Financial: John Williamson
🗹
Date of Update
1/23/18

## Slide 7: Issues / Risks Log (Example)
Classification | Description | Mitigation Plan | Assignee | Target Date
Risk | Contractors may not be on board in time to develop hardened platform per plan | Product to go in front of IT prioritization committee to address need for contractors | Product | 1/23/18
Issue | User can generate results that are incorrect by using non-designed workflow. This is a platform limitation around which we cannot design. | Gather snapshots from right and wrong methods and provide to Product Incorporate snapshots and correct procedure into training Train users on appropriate procedure and risks of wrong procedure | J. Smith (Data Science) T. Jones (Product) T. Jones (Product) | 1/26/18 2/2/18 2/9/18

## Slide 8: Project Description (Example)
Project Name: nH Match
Description:
Create a decision support tool for Discharge Planning (integrated into nH Discharge, nH Coordinate, or both) to display the top SNFs for a patient’s specific needs based on: Case 1: historical performance for similar patients when sufficient nH market data are available Case 2: the nH Perform score of SNFs when either: insufficient nH market data are available, or Predict assessment was not conducted
Goals / Value:
Provide decision makers a framework for identifying SNFs with potential for best outcomes for the patient, tailored for each patient’s needs if market data are available, else using publicly available data (nH Perform) Reduce readmissions Reduce SNF LOS Improved patient satisfaction Improved contract performance
Customers/users:
Customers: Health systems, health plans, ACOs. Internal customers (e.g., ICCs / BPCI program) Users: Discharge Planning Team, ICCs
Use cases (include who the users are):
When creating discharge plan for a patient going to a SNF, the application will automatically read the patient’s Impairment Group, Age, Gender, and Acute BM, DA, and AC. If desired, the discharge planner will modify the default address and/or search radius. The system will generate the results per the two cases given in the “Description”. These results will be used by the discharge planning team to help inform the decision of the next care setting.
In-Scope:
Creation of a working mockup / proof of concept to be approved for product development. Selection of factors, including severity adjusters (current factors shown in “Use Cases”). Actual factors TBD based on discussions w/ clinical subject matter experts. Results: Primary focus: nH Market results (where sufficient records exist); Secondary focus: nH Perform results Integration methodology and platform (e.g., Discharge)
Out-of-Scope:
Scope TBD:
DRG and/or other severity adjusters for nH Perform results